## Project Plan
Project Plan for Old GF with GDPR | [6 empty] | 2018-10-23 |  | 2018-10-24 |  | 2018-10-25 |  | 2018-10-26 |  | 2018-10-27 |  | 2018-10-28 |  | 2018-10-29 |  | 2018-10-30 |  | 2018-10-31 |  | 2018-11-01 |  | 2018-11-02 |  | 2018-11-03 |  | 2018-11-04 |  | 2018-11-05 |  | 2018-11-06 |  | 2018-11-07 |  | 2018-11-08 |  | 2018-11-09 |  | 2018-11-10 |  | 2018-11-11 |  | 2018-11-12 |  | 2018-11-13 |  | 2018-11-14 |  | 2018-11-15 |  | 2018-11-16 |  | 2018-11-17 |  | 2018-11-18 |  | 2018-11-19
[7 empty] | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun
| Task Name | Duration(IOS) | Duration(Android) | Start | Finish | Priority | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM
1 | Login sheet
1.1 | Check UI Document | 1 | 1 | 2018-10-25 | 2018-10-25 | 1
1.2 | Modify Welcome Page | 0.5 | 0.5 | 2018-10-27 | 2018-10-27 | 2
1.3 | Develop Start Screen of first time | 1.5 | 1.5 | 2018-10-30 | 2018-10-31 | 2
1.5 | Modify the Creat Account page | 1.5 | 1.5 | 2018-10-31 | 2018-11-01 | 2
1.6 | Develop the UserRightsInfromation page | 1 | 1 | 2018-11-02 | 2018-11-02 | 2
1.7 | Develop API of Concent page to backend | 1 | 1 | 2018-11-03 | 2018-11-03 | 2
1.8 | Develop Concert page | 1.5 | 1.5 | 2018-11-06 | 2018-11-07 | 2
1.9 | Develop UserLicens page | 1 | 1 | 2018-11-07 | 2018-11-08 | 2
1.1 | Modify the Log in page | 1 | 1 | 2018-11-09 | 2018-11-09 | 2
2 | Backend comunication
2.1 | Access SMS Service to the backend | 0.75 | 0.75 | 2018-10-26 | 2018-10-26 | 1
2.2 | Modify API to the backend on Creat Account page | 0.75 | 0.75 | 2018-10-26 | 2018-10-27 | 1
3 | Test
3.1 | Developer Test + Joint Test | 2 | 2 | 2018-11-09 | 2018-11-13 | 3
3.2 | Issue Settle | 1 | 1 | 2018-11-13 | 2018-11-14 | 3
4 | Delivery
4.1 | Pubulish on-line | 1 | 1 | 2018-11-14 | 2018-11-15
| Working Day for Development + Test: | 14.5 | 14.5

## General
Project：Old GG with GDPR
Time：11th Oct, 2018
Ver：01
Product Manager：Angela Zhou
Module |  | 状态
Login sheet | 19 | To be discussed | 4
Backend comunication | 4 | Deploying | 0
| 0 | TBD | 21
| 0 | Reject | 0
| 0 | Done
0
0
Test | 2
Knowledge Base(TBD) | 0
Total
25

## Functional List
Project：Old GG with GDPR
Time：11th Oct, 2018
Ver：01
Product Manager： Angela Zhou
Working Day
No, | Module | Sub-module | Function name | Funtion Details | Priority(1-3) | Status | Engineer | Remark | iOS | android
1 | Login sheet | UI | 拿到UI素材后检查 Check UI document | iOS/ Android | 1 | Deploying | Karl |  | 1 | 1
2 | Login sheet | Welcome Page | 启动页的开发修改(iOS) Modify Welcome Page for iOS |  | 2 | TBD | Tim |  | 0.5
3 | Login sheet | Welcome Page | 启动页的开发修改(Android) Modify Welcome Page for Android |  | 2 | TBD | Kyrie |  |  | 0.5
4 | Login sheet | Start Screen of first time | 第一次运行APP时，临时首页的开发(iOS) Develop Start Screen of first time for iOS |  | 2 | TBD | Tim |  | 1.5
5 | Login sheet | Start Screen of first time | 第一次运行APP时，临时首页的开发(Android) Develop Start Screen of first time for Android |  | 2 | TBD | Kyrie |  |  | 1.5
6 | Backend comunication | SMS Service | SMS服务的接入（主要是后端，前端调用） Access SMS Service to the backend, and connect to APP of iOS |  | 1 | TBD | Tim |  | 0.75
7 | Backend comunication | SMS Service | SMS服务的接入（主要是后端，前端调用） Access SMS Service to the backend, and connect to APP of Android |  | 1 | TBD | Kyrie |  |  | 0.75
8 | Backend comunication | Create Account | CreateAccount页的后台接口修改 (iOS) Modify API to the backend on Creat Account page for iOS |  | 1 | TBD | Tim |  | 0.75
9 | Backend comunication | Create Account | CreateAccount页的后台接口修改 (Android） Modify API to the backend on Creat Account page for Android |  | 1 | TBD | Kyrie |  |  | 0.75
10 | Login sheet | Create Account | CreateAccount页的修改开发（iOS) Modify the Creat Account page for iOS | Ask the user to enter • picture/avatar • e-mail =(will be the username) • incl. the mail verificationcode • chose a password (enter this 2 times) • Name • Mobile Phone nr • incl the SMS verificationscode • Address line 1 and 2 • zip-code • CityTown • Region/State • Country Question: Is there to add a Optional function for some items? | 2 | To be discussed | Tim |  | 1.5
11 | Login sheet | Create Account | CreateAccount页的修改开发（Android） Modify the Creat Account page for Android | Ask the user to enter • picture/avatar • e-mail =(will be the username) • incl. the mail verificationcode • chose a password (enter this 2 times) • Name • Mobile Phone nr • incl the SMS verificationscode • Address line 1 and 2 • zip-code • Town • Region • Nationality | 2 | TBD | Kyrie |  |  | 1.5
12 | Login sheet | User Rights Infromation | UserRightsInfromation的开发（IOS） Develop the UserRightsInfromation page for iOS |  | 2 | TBD | Tim |  | 1
13 | Login sheet | User Rights Infromation | UserRightsInfromation的开发（Android） Develop the UserRightsInfromation page for Android |  | 2 | TBD | Kyrie |  |  | 1
14 | Login sheet | Concent | Concent页的后端接口的开发 (IOS） Develop API of Concent page to backend for iOS |  | 2 | TBD | Tim |  | 1
15 | Login sheet | Concent | Concent页的后端接口的开发 (Android） Develop API of Concent page to backend for Android |  | 2 | TBD | Kyrie |  |  | 1
16 | Login sheet | Concent | Concent页的开发(iOS) Develop Concert page for iOS |  | 2 | TBD | Tim |  | 1.5
17 | Login sheet | Concent | Concent页的开发(Android) Develop Concert page for Android |  | 2 | TBD | Kyrie |  |  | 1.5
18 | Login sheet | User Licens | UserLicens页的开发（iOS) Develop UserLicens page for iOS |  | 2 | TBD | Tim |  | 1
19 | Login sheet | User Licens | UserLicens页的开发（Android) Develop UserLicens page for Android |  | 2 | TBD | Kyrie |  |  | 1
20 | Login sheet | Log in Page | 真正首页的开发修改（iOS) Modify the Log in page for iOS | Enter the mobile number and Password to login | 2 | TBD | Tim |  | 1
21 | Login sheet | Log in Page | 真正首页的开发修改（Android) Modify the Log in page for Android | Enter the Account ID and Password to login | 2 | TBD | Kyrie |  |  | 1
22 | Test | Test | Developer Test + Joint Test |  | 3 | TBD | Martin |  | 2 | 2
23 | Test | Test | Issue Settle |  | 3 | TBD | Martin |  | 1 | 1
Remark Priority(1-3): 1 is the most urgent. | [8 empty] | 14.5 | 14.5

## 需求属性说明 (hidden)
需求属性 | 属性说明
编号 | 需求的顺序号，唯一性标识
提交人(*) | 需求的录入PD，负责解释需求
提交时间 | 需求的录入时间，辅助信息
模块(*) | 根据产品的模块划分
名称(*) | 用简洁的短语描述需求
描述(*) | 需求描述：无歧义、完整性、一致性、可测试等
提出者 | 即需求的原始提出者，有疑惑时便于追溯
提出时间 | 原始需求的获得时间，辅助信息
Bug编号 | 一些Bug视为需求，统一管理
分类 | 新增功能、功能改进、体验提升、Bug修复、内部需求等
层次 | 基础、扩展（期望需求）、增值（兴奋需求）
重要性 | 重要程度，辅助确定商业价值
紧迫度 | 紧急程度，辅助确定商业价值
持续时间 | 持续时间，辅助确定商业价值
商业价值(*) | 商业优先级，不考虑实现难度，群体决策
开发量(*) | 需求的开发工作量，表征实现难度
性价比(*) | “商业价值/开发量”，用于决定先做哪个
状态(*) | 需求生命周期：待讨论、暂缓、拒绝、需求中、开发中、已发布
负责PD(*) | 状态进入“需求中”后确定
开发工程师 | 状态进入“开发中”后确定
项目名称 | 需求的发布项目
发布时间 | 需求的发布时间
备注 | 其它任何信息，如： 1.被拒绝的理由 2.被暂缓的理由和重启条件 3.其它相关文档 ……